## Clarifications (hidden)
Ref | Clarification | EMIS Response | NHS Digital Comments 06/03/2018 | InVision Response | Microtest Response | TPP Response | Date Raised | Status | Date Closed
GPSoC0010 | Can GPSS provide Practice Code (as a proxy Pooled List Code) instead of GP-Local Code in GP-Links requests (See GPSoC0001) | No, Practice Code can’t be used in place of GP-Local Code. | Thanks for the clarification. Would it be practicable to change the GPS to accommodate this i.e. always send the GP Practice code associated with a GP-Local Code in a GP-Links message (Note this is for GP-Links message only, not on the GPS database?) |  | This is possible, but would be subject to a CCN
GPSoC0001 | What validation is performed by GP Systems on the GP Local code contained in the incoming GP Links message? What is the consequence of any potential validation check failing | The GP System accepts even if the ‘GP Local Code’ contained in the incoming message doesn’t match with any of the GP Codes available with the GP System. So there is no validation performed against the incoming message for its GP Local Code. |  |  | There is currently no validation on the GMC Number / Local Code in place when processing individual incoming transactions. |  |  |  |  | All
GPSoC0002 | Please clarify how the GMC Code for a Pooled List GP is set. (Is the value agreed with PCS) | The GMC code for a pooled GP List accepts any numbers up to 7 digits. Current workflow functionality, upto the site to get their own GMC code and manage the pooled list and any agreement themselves |  |  | The GMC number for a pooled GP is mutually agreed with PCSE. Normally, this is set to 9999999 |  |  |  |  | EMIS
GPSoC0003 | Is the GMC code value stored and the GP-Links messages received from NHAIS / Convertor validated to check the GMC Code as they are using is the same? (Pooled List and non-Pooled List) | No, the GP-Links messages received from NHAIS/Convertor are not validated for matching message’s GMC code with the ‘GMC Code stored’. |  |  | No |  |  |  |  | TPP
GPSoC0004 | In GP-Links message responses does the GMC Code used by NHAIS / Convertor have to correspond to the value used in the request? (Pooled List and non-Pooled List) | No, GP-Links message responses from NHAIS/Convertor don't have to have GMC Code corresponding to its request. |  |  | No |  |  |  |  | Microtest
GPSoC0005 | The simplest scenario would be for Spine to set GMC Code to a default (say “9999999”) in all outbound messaging (for responses and unsolicited) both for Pooled List “Practitioners”? and for real Practitioners (e.g. if we have some frozen local codes still in use) – would this work? | Not really feasible to answer as we would need to understand the broader context, our answer here is much the same as the response from Microtest. | Thanks, clarifying the question, the context here is what Spine sends in the GP-Links messages (Approvals, Amendments, Deductions etc) not what is stored in the GP System Database, given EMIS answers to 1, 2,3,4, it suggests that what the GPS receives is not validated and does not need to be consistent with (e.g.) a corresponding ACG registration or what the GPS holds for the patient, therefore if we send everything the same e.g. GP Local Code 101, GMC Code 9999999 would this cause an issue? Note our current assumption is that we will default outbound transactions to use to a single known value that is distinct and valid for the practice, but if we can simplify our solution / understand possible impacts that may be desireable. Action: EMIS to verify if Spine sending a GP Links message containing a GP Practice Code instead of a GP Local Code or a GP Local Code associated with the Practice rather than the GP Local Code specific to the patient will result in an exception in the GP System. Assumption: Spine will send a GP Local Code which is valid for that GP Practice, but this may not be the code that the GP System holds/included in the message to Spine for that patient. |  | No it wouldn't GMC codes must be unique. If a Pooled GP is employed, then they are set up as a ficticious user on the practice's user database. Evolution would not allow the same GMC code to be used for both a real and ficticious user. PH – Microtest confirmed that they must send unique codes in outging messages, but do not validate the values contained in incoming messages |  |  |  |  | NHS Digital
GPSoC0006 | In the scenario where one transaction was invalid in an interchange with multiple messages and transactions, could PCRM process the valid transactions and reject the single invalid transaction? How would the GP Systems handle the scenario? | 1) If one transaction is invalid with format, the GP system fails all the transactions associated with the interchange. 2) If one transaction is invalid with data, GP System fails only that particular transaction and passes other valid transactions from the interchange. We can track these details from ‘View Interchange History’ tab. | Thanks, additionally, can you clarify how does the GPS handle the invalid interchange? - Are RECEP messages including failure states generated - is there a manual operational response i.e. a telephone call Action: EMIS to verify and confirm reporting of failed interchanges by the GP System. Assumption: Spine to GP System - GP System notifies the Practice - GP System does not return a receipt report (RECEP) failure message to NHAIS/Spine - The GP Practice calls EMIS, who use the Interchange audit history to resolve the issue GP System to Spine - Spine detects an interchange exception and creates an entry in the interchange audit log - No receipt report (RECEP) failure message is sent to the GP System - PCSE are notified |  | No - the whole interchange is rejected PH - Microtest advice is that we do not alter the existing mechanism as doing so would add unneccessary complexity. If GPSS resends a partially processed interchange this could lead to an issue with interchange sequence numbers |  |  |  |  | Vision
GPSoC0013 | Can GPSS receive / send interchanges sent in real time or do these have to be batched and sent to schedule Clarification could be extended to:- Is the GPSS sensitive to transactions being split over multiple interchanges i.e. The convertor may generate messages and responses in real time such that it will send same volume of transactions sent but in an increased number of interactions/messages? [NM 04/12/2017] Note this is not a requirement to change to GPSS behaviour rather it will be a difference between how NHAIS and Spine will work.The GPSS can control when it receives messages via MESH Polling? [NM 05/01/2018] Design Assumption is that Spine will send unsolicited outbound in real time as created on Spine, this will result in single transaction interchanges. The GPSS can poll for these messages as per the existing schedule. | GPSS receive/send interchanges in schedule manner through batches. Because ‘DTS Service Transmission’ runs for every 10 minutes. For the extended clarification needed, the GPSS is not sensitive for the transactions being split over multiple interchanges and even with increased/decreased number of interactions/messages. | Conclusion: GP System will have no issue processing real time (not batched) GP Links interchanges. GPSS requested message profiles. |  | This is possible, but would be subject to a CCN. I would suggest that whilst sending in "real time" would be OK, configuring the MESH client (or API) to constantly poll for received interchanges would be inefficient and possibly detremental to N3 link performance. PH - Microtest advise that to change this would add increase complexity for minimal gain.
GPSoC0014 | Can Spine Convertor auto notify interchange failures to GPSS e.g. via MESH or e-mail | We haven't heard of Spine Converter - if we were to receive an interchange failure message this will likely be handle as an unknown message type and drop into error in the DTS transmission history - We do handle the current MESH RECEP message | The Spine "convertor" is the name for the Spine component that will handle GP-Links messages. The question relates to the possible automation of failure notifications that may be manually raised with the GPSS rather than handling the RECEP messages (below) Conclusion: Automatic Failure Notification to GP System Suppliers could be implemented via MESH - This would provide benefit to both PCS and the GP System Suppliers |  | We are already notified of interchange failures though the receiving of an incoming RECEP interchange (stating successful or unsuccessful translation of outgoing data) PH - Microtest confirmed that they would benefit from receiving a copy of interchange failures, but being able to identify the supplier may be difficult as this would require Spine to have the mapping of GP Practice to supplier (Tracking Database) NM - What is the Tracking database – I would have thought we would identify the supplier from SDS – Are these kept in Sync? We need to broaden this question to include other issues e.g. out of sequence warnings where a +ve Recep interchange is sent to the out of sequence message, and possibly other PCS / GPSS comms RT - The NHS Digital's GPSoC National Tracking Database is the authoritive location where the services offered by, and the supplier of a clinical system of, one or more Practices may be ascertained
GPSoC0018 | Can GPSS receive interchange processing reports, such as sequnce warning report, interchange receipt report and interchange exception report? | As of our knowledge, we don’t think we receive.[MAN: If sent this would drop into unhandled] | Thanks. To be clear, this question would apply to the GPS consuming RECEP messages from NHAIS / Spine Do you expect these? Do you utilise them? Both Successes and Failures? Assumption: RECEP failure messages are not consumed by the GPSS EMIS: to check and confirm EMIS do use these - how do they use them? |  | The user is presented with these warning on the practice system. Ultimmately, interchange sequence warnings should be dealt with tby the Practice through the UI - not by the GPSS. I can't see that this is something that we would look to become involved with! NM [04/12/2017] I am unclear as to the mechanism for NHAIS communicating an interchange failure is this a Receipt Report indicating failure, the absence of Receipt report indicating success? or a failure notified via another route - e.g. email, fax?
GPSoC0020 | Does your Practice System make use of HA receipt reports? - Interchange Successes? - Interchange Failures? (NM 05/01/2018 - Are these ever received - no evidence that NHAIS sends) - Within Interchange Failures reports, are the outcomes for individual messages differentiated? What does the Practice System do with an Interchange Failure? What would be the impact of not sending these receipt reports? | Assuming here we’re talking about DTS Transmission Report from GPSS side, 1) We’re capturing Successes and failures 2) Within Interchange Failure Reports, the outcomes for individual messages are differentiated. 3) It allows the user to reprocess the failed interchanges. | Thanks. To avoid overlap with #18, this question should consider the GPS Sending RECEP messages to NHAIS / Spine So does the GPSS generate RECEP messages for when processing GP-Links messages from SPine / NHAIS - both success and failure? Re response 3) Can the GPSS (relating to received interchanges) can the GPSS process a duplicate interchange? Assumption: RECEP failure messages are not generated by the GPSS in response to interchange failures. EMIS: to check and confirm |  | Yes. Interchange successes are quietly written to the "Network Stage Reports". However, if a translation failure is received, a Links "mail" message is reported to the Links clerk at the Practice The Practices would normally contact their GPSS to reolve this issue (the nature of the problem usually precludes user resolution themselves) The RECEP report contains minimal details of the reason for translation failure (i.e. which message is at fault). Theoretically the translation failure that is faxed / emailed to a pracitce should correlate the an invalid receipt report received within the RECEP message. Missing these messages could result in data not being sent to the HA (and thus a lack of payment, practices waiting for notes, addresses not being updated on NHAIS for centralised services, etc.)
GPSoC0007 | How is close of quarter communicated by NHAIS to GP Systems? What action does this trigger on the GP System? | This will create a task in the Gplinks Close Quarter Inbox based on the ‘Trading Partner Code’ received from incoming message, which we can also manually process based on the age of transaction in the Close quarter task list. | Thanks, additionally, can you clarify what will happen if the GPS ceases to receives these (because they may not be required for the new payments solution) i.e. the Quarter is never closed Conclusion: The GP System will continue to function if Spine does not send a GP Links F8 End of Quarter marker message. There will be no impact on the operation of the GP System |  | NHAIS sends a QEM (Quarter End Marker) transaction to the practice within a REGIS EDIFACT message. PH - Microtest to send edifact specification for REGIS transactions. RT - Apologies - please find attached to this email
GPSoC0021 | Potentially, when the GP Payment function is transitioned off NHAIS to Capita, and the feed of registered patients supplied by Spine, there may be no need to process registrations differently at quarter end. In this case, would GP Systems still require a period end message from PCRM? | We will need to look into and feedback. | Assumption: Not an impact if End of Quarter message not sent
GPSoC0008 | What validation is is performed by GPSS on the NHAIS Posting (HA) sent in - For responses - Does it need to correspond to the one used in the request - For X-Border can it come from the 'other' NHAIS for the Patient i.e. A Welsh Resident maight have updates sent by an English NHAIS | According to the ‘Transaction Types’ in the Response, it validates the appropriate message segments and actions the response, it doesn’t always validates all the message segments. For example, any transactions other than ‘New Registration Approvals/Rejections’ are processed in with just matching ‘Patient Identifier’. For ‘New Registration Approvals/Rejections’, the response must have the same ‘Transaction Number’ that is sent in request. Unsure regarding X Boarder - MAN: There is no link to Scotland or NI as it is MESH based.Therefore only applies to Wales/England x border. In this scenariowe do no additional checks / validation to within border(i.e. syntax validation etc) | Thanks. The question context here is Fringe practices which could be across NHAIS area bondaries and are therefore connected to two NHAIS systems. This includes the English / Welsh Fringe. So to illustrate, for a practice connected to two NHAIS say "WR" and "GWE" if the the GPS sends a ACG Ref 001 to GWE, would it link an APF Ref 001 from WR to the same request? In theory the Practice may have sent the same transaction ref to both NHAIS systems so the response can only be linked to the correct request using Transaction Number & FHSA? Action: EMIS to verify how the GP System uniquely identifies messages in the case where the GP Practice has multiple trading partners. |  | Tthe response received from NHAIS must match for transaction number (for Approvals only) or NHS number (for all other transactions). We do not currently have any experience of English / Welsh cross border transfers. PH - NHAIS posting not validated by GPSS on incoming messages NM - I am not as optimistic as Pete as I read the highlighted text as Microtest possibly saying for everything but approvals the NHAIS Posting / HA Cipher must be correct for the NHS Number. This is just as applicable in English Regional Fringe scenarios as it is in England / Wales X-Border. i.e. in a Fringe situation the GP system knows which are ‘Devon’ patients and which are ‘Cornwall’ patients and we have to provide the corresponding Posting? (We should amend the question so we say X-Border or Fringe and also change the i.e. where a practice is connected to multiple HAs a resident in one HA may have a new transaction / response sent by another HA. If this is true we may want to ask as to the cost of changing this to not validate Posting. (Other supplier responses may similarly lead to CCN requests)
GPSoC0009 | Can the GPSS change so that for ammendments partial records are not sent to data objects e.g. whole of name or whole of addresss is sent, not just surname, or line 1 | GPSS also sends the partial amendments records being made to the data objects. | To clarify the question context here. i) Spine unlike NHAIS will always send all elements of a Name and Address in an amendment message So if a PCS change an address (on Spine) from Line 1 - SPRING COTTAGE Line 2 - Line 3 - LOWER SNORING Line 4 - ANYTOWN Line 5 - Post Code - AA1 1AA To Line 1 - ROSE COTTAGE Line 2 - Line 3 - LOWER SNORING Line 4 - ANYTOWN Line 5 - Post Code - AA1 1AA Spine will send all elements of the address address in a GP-Links Amendment, not just the building name: NAD+PAT+ROSE COTTAGE:$:LOWER SNORING:ANYTOWN:$++++AA1 1AA' ii) Could the GP System be changed to do the same i.e. to always send all elements?. Conclusion: GP System can accept the full address from Spine to communicate address updates. The GP System would benefit from also receiving the SCN relating to the address change from Spine. The GP Links specification currently has no facility to contain the SCN, but it could possibly be supplied using a spare field. Cnange Request EMIS to verify if the whole address is sent to Spine from the GP System. If not, a change request may be required to ensure that the whole address is always sent for all address updates. |  | This is possible, but would be subject to a CCN
GPSoC0016 | Can GPSS enforce validation v PAF for address updates | No, we’re enforcing any validation on Patient Address Fields(PAF) for address updates. | Thanks. Can you confirm your response i.e.that all address updates from the Practice are validated against PAF Action: EMIS to verify options for validation of address updates on the GP System. PAF is not used but possibility of using an open source address look up solution |  | We currently don't operate any integration with a PAF. This would incur a development cost and (almost certainly) a license fee from a PAF supplier (Word Apak for example)
GPSoC0011 | Can GPSS constrain what is sent in RI code field - Could Only ODS Org Codes be sent - Could only agreed generic national codes be sent | Assuming RI as ‘Residential Institute Code’, If the incoming message’s ‘RI code’ field value doesn’t match with the Trading Partner’s RI Code in the GPSS, it prompts the user with the message that RI Code doesn’t match. So that, User is restricted to perform any action on the task. We don't format validate the content of the field, any value could be sent | Thanks for the clarification. Would it be practicable for the GPS be changed to enforce the use of a restricted set of RI Codes at a Practice i.e.. "STU" and "CARE"? Conclusion: - GP System does not validate/check/contrain the values populated in the RI field on outbound GP Links messages. - Gp System does validate that the RI code supplied on inbound messages is valid for the Trading Partner (NHAIS System). - This will not prevent the adoption of simplified codes for care home residents (care) and students (stu), but will present a challenge on transition as patients with Local NHAIS codes indicating care home resident will need to be converted to 'care' Change Request: For GP Systems to lock down RI codes entered to a limited set |  | This is possible, but would be subject to a CCN
GPSoC0012 | Can GPSS constrain what is sent in Free Text field (Structured text only), no superficial notes e.g. "Please send MRE" | GPSS doesn’t constrain any Free Text that is sent in. | Thanks for the clarification.Would it be practicable for the the GPS be changed to enforce the use of a restricted set of Text messages Change Request: It will require a change request for the GP System to implement a standard list of common GP Notes as a single select list |  | This is possible, but would be subject to a CCN
GPSoC0015 | Can GPSS enforce GP-Links / Spine Message intergirity i.e. if PC code change on Spine will always result in a GP-Links Reg Message | We understand this question like if the PC code on the Spine changes, will this affect GPLinks Reg Workflow. If so, then the change in PC code on Spine doesn’t affect GPLinks Reg Workflow. This is because the GPLinks Reg Workflow doesn’t involve PC code in the any of the messages. | To clarify the question. The background here is that there are concerns with discrepancies between SPine and NHAIS data and can the GPSS help better enforce integrity. The benefits of this would acrue now, ahead of NHAIS decomissioning and may help mitigate issues in the transition of services off NHAIS e.g. if a Primary Care Code is changed on Spine the GPS always registers the patient via GP-Links (and visa versa) equally if the GP Practice updates (or synchronises with) a Spine address the GPS always amends the patient address via GP-Links (and visa versa) Additionally: Would it be an issue if Spine ignored amendments to name and address via GP-Links and relied on the HL7 message> Action: EMIS to verify if GP System emforces integrity between Spine direct message update and GP Links update System sends both triggered from a single action |  | We currently don't generate an AMF as a result of accepting a Spine update. This is possible, but would be subject to a CCN
GPSoC0017 | PCRM would like to provide FP69 notifications with a reason code of 8 supported by an appropriate description. Would this provide an acceptable user experience for GP Practices using your system? | The GP System shows the appropriate description for the code that is sent in with FP69 notifications. For example, for the reason code of 8, it shows ‘Other Reason’. | Action: EMIS to confirm if the free text reason, supplied in the GP Links message to supplement the FP69 Reason Code of 8 (Other), is displayed in the GP System System shows description Action: EMIS to provide indication of effort required to introduce new FP69 reason codes. |  | This would not present a problem to the functionality of the GP links system as it currently stands. I also do not see why it would adversely affect a user in any way.
GPSoC0019 | Could GP Practices populate the previous HA Cipher in a registration acceptance request with a value that represented the patients previous administrative area (i.e. Eng, Cym, IoM, HJ, DMS, NI, Sco) (Wales code = CYM) | Yes, ‘Registration Acceptance Request’ is populated with ‘Previous HA Cipher’, when applicable. | Thanks. Could the GPS be changed to enforce this for transfers i.e. force the user to enter a previous administrative area from a fixed list Action: EMIS to provide confirmation of whether the system would be able to restrict the entry of previous NHAIS cypher to selection from a fixed list List currently used would need to be reduced |  | It could. However, this is currently the local area (e.q. CR, DN, SM (for Cornwall, Devon and Somerset repesctively). So, we could set up HATP Organistations that are "nation bound" - that would not present a problem
GPSoC0022 | Is it currently possible for GP Practices to re-use a transaction number when submitting an updated GP Links message? If so, could the GP System be updated to prevent this action, so that Spine could be sure that any duplicate detected is actually a duplicate? | It’s not possible to re-use the ‘Transaction Number’ for GpLinks messages.
GPSoC0023 | When GP practices receive an Amendment In from PCS on their GP Links screen, what steps are taken to update the patient information held on the GP System? Does it auto-update as soon as the user 'Accepts' the amendment, is there a method of rejecting the amendment? Or are manual steps taken as a result of the notification?
GPSoC0024 | Are GPSS ok to use MESH as a way of storing GP-Links messages rather than for NHAIS to set the Practice as unavailable and for these to be stored to be sent by Spine Spine? Mesh can store up to 5d(?) messages on line plus up to a month via s service request to replay.
GPSoC0025 | Do GPSS use the Posting value held on Spine when generating GP Links amendments and removals (deductions)?
GPSoC0026 | Can GPSS always provide a full BEF date when processing a patients registration when submitting on Spine (via Spine messaging). This was requested for Capita MRE processing
GPSoC0027 | There are currently nine sets of Merged Practices using the same Link Code. What is the purpose of this set up? Could the GPSS reconfigure these so each Practice has its own Link Code ahead of transition. |  | Conclusion: Spine can identify practices merged onto a common link code by using the GP Local Code supplied in the GP Link message and mapping to the associated Practice Code
GPSoC0028 | Does your Practice System perform any character set validation on data items sent in GP Links messages from NHAIS? |  | Conclusion: Spine will force GP-Links outputs to Upper Case.
GPSoC0029 | Does your Practice System expect the title field contained in a GP Links transaction sent by NHAIS to contain a value defined in a set list of standard titles? Is any validation applied to this field? |  | Action: EMIS to confirm that incoming messages are not validated based on a pre-defined list of valid titles No validation
GPSoC0030 | Does your Practice System utilise & send GP-Links Receipt Failure reports as the primary mechanism for communicating that a GP-Links interchange has been rejected
GPSoC0031 | Do GPSS utilise or validate the GP-Links Source MESH Mailbox and / or Source Link code |  | Conclusion: Spine will spoof the NHAIS MESH mailbox
GPSoC0032 | How does the GPSS handle duplicate interchange sequence numbers?(interchange control reference number) ie two separate interchanges with different payloads using the same number Does this ever happen now? Can / could the GPSS handle rare occurrences of such duplicates (e.g. manually resubmit and process ) The same query extends to duplicate message and transaction numbers. |  | Conclusion: Duplicate interchanges sent to interchange history - GP Practice acknowledges to resolve Message sequence number not checked for duplicates Duplicate Transactions would not be applied.
GPSoC0033 | Could Spine utilise a unique but non-sequential interchange control reference for GP-Links messages sent by Spine this would be used for duplicate detection but not sequencing (i.e. drop the requirements based on sequencing) The same query extends to message sequence number and transaction number. Could this be done in a phased transitional period i.e supporting as-is behaviour with some NHAIS systems but new behaviour when interfacing with Spine for GP-Links messages to NHAIS sites that have been decommissioned. |  | Conclusion: Duplicate interchanges & transcations sent to unmatched box - not applied Spine will use a mechanism to ensure that we will not send a two different payloads with the same interchange control number
GPSoC0034 | Are there any English GP Practice systems that are not using Spine PDS Messaging (i.e. the HL7 message set)? |  | Conclusion: EMIS confirmed that they do not have any Practice in England that use GP Links but no Direct Spine messaging
GPSoC0035 | GP Practice use a number of mechanisms to request an out of area removal, these include: REG message, DER message with reason of OOA, AMG message with address update and free text indicating patient OOA Ideally these processes would be standardised to use a single message type. Could this be achieved? |  | Conclusion: No benefit in restricting the current use of GP Links messages. It would be more practical to implement these process changes when the GP Links convertor is replaced
GPSoC0036 | The edifact specification allows 22 reasons for deduction to be communicated from GP to NHAIS via a DER message but only 3 of these codes are currently utlised, with Type 13 (O/R) being supplemented with a GP supplied reason in the General Notes. Would it be possible to utilise more of the 22 reason codes in the GP System interface so that there is less reliance on GP Notes, thus allowing more DER requests to be processed systematically. |  | Action: EMIS to verify if the GP System can be updated to implement additional GP Links removal type code over and above the 3 currently used (1, 2, 13). This would request a change request to implement
GPSoC0037 | How does the GPSS utilise the information currently provided in a DEF Dedcution from the HA to the Practice Does the GPSS process the Removal Reason - how is it used Does the GPSS process the New HA - how is it used Specifically - is the GPSS sensitive to new HA Values if these were to be provided (such as ENG to represent a patient resident in England) - is the new HA ustilised in the "Code 6. New HA / Same GP" scenario |  | Conclusion: GP System does not validate the the removal reason but does display the details of the deductions
GPSoC0038 | Does the GPSS always handle the new HA / same GP secnario by sending a an address amendment (anticipating a deduction response) Will the same address amendment always be sent to Spine via a direct HL7 message |  | Conclusion: EMIS GP System will always initiate a deduction and re-registration in this case
GPSoC0039 | When a patient changes between a normal GMS and a Practice of Choice registration is this ever enacted via an GP-Links amendment message (e.g. using the corresponding free text strings for an OOA registratioin) or is PoC only ever sent via a registration (so a patient must be deducted first then re-registered) The same question applies in reverse can a patient moving back into area be communicated to the HA via an amendment message |  | Action: EMIS to verify if the update following a patient moving out of Practice area and registering with their existing GP Practice under the Practice of Choice scheme can be restricted to the GP System, thus avoiding a removal and re-registration on Spine Agree not to change the work flow
GPSoC0040 | Does the GPSS validate the sending FHSA as provided in the NAD segment of a GP-Links message. i.e. The GPSS validates that the GP-Links EDIFact message come from a HA that is known to the GP Practice System. the FHSA must be consistent with the Source Link Code provided in the UNB segment of the GP-Links EDIfact interchange | GP Practice are required to set up their trading partners on the system. Practice are alerted if they receive an interchange from a trading partner not configured for their GP Practice
GPSoC0041 | Do GPSS utilise GP-Links Receipt Report (RECEP) "Success" messages sent by NHAIS to the GPSS | Success and failure messages both
GPSoC0042 | Do GPSS send GP-LInks Receipt Report "Success" (RECEP) messages to NHAIS when an interchange has been successfully processed
GPSoC0043 | ?
GPSoC0044 | The receipt of deduction request (DER) GP Links message, may trigger one of the following events in NHAIS: - If the DER request results in an immediate removal of the patient from primary care, NHAIS will return a Deduction (DEF) GP Links message to GPSS to confirm the deduction. - If the DER request will result in a future removal of the patient from primary care, NHAIS will return a Deduction Rejection (DDR) GP Links message to GPSS to confirm receipt of the Deduction Request (DER). NHAIS will then send a Deduction (DEF) GP Links message at the time of deduction. - If the DER request is rejected by PCS, NHAIS returns a Deduction Rejection (DDR) GP Links message to notify the GPSS that the deduction request has been rejected. In the scenarios above, NHAIS is returning a Deduction Rejection (DDR) GP Links message to communicate two different outcomes, a rejection of the deduction and a future deduction. How does GPSS interpret this message? Does the receipt of this message trigger any activity on GPSS?
GPSoC0045 | Further to the clarification GPSoC044, GPSS may sometimes send a Removal Out of Area (REG) GP Links message to request the deduction of a patient because they have removed out of area. We beleive this message effectively duplicates a DER request with reason of O/R containing a GP Notes description of 'out of area'. Currently NHAIS adds all REG messages to BOAJ report, but we would like to process REG messages the same way as DER messages. If Spine returned a Deduction Rejection (DDR) message in response to an REG message in the same way as it would if it received a DER message requiring a future dated removal, would this cause a problem for GPSS? | The DRR will sit in the Practices deduction reject queue.
GPSoC0046 | We received the following the following advice from PCSE, please could you provide some clarification of the process behind this system behaviour? "a snippet of the message received when a patients NHS number has been invalidated on Spine and a re-registration is sent through to PCSE via GP links. As I mentioned this appears to happen the day after the NHS number is invalidated by NBO and limited to EMIS practices. Unfortunately the number of characters allowed in the free text field is not enough to accommodate the full message but it is always the same indicating a system not human driven process. The ‘Rec’d NHS number = xxx xxx xxxx’ is an NHAIS generated message because the practice have supplied an invalid NHS number in the GP links transaction." | No system feature to actively look for these updates
GPSoC0047 | Do GPSS capture patient organ and blood donor preference | Content code populated so possibly use GPES
GPSoC0048 | How frequent does GPSS poll the mailbox for inbound interchanges?
GPSoC0049 | How frequent does GPSS send outbound interchanges?

## Consolidated Position (hidden)
UID | Clarification Subject | Assumed Position | Potential Change Request (High Priority Highlighted in BOLD) | EMIS | Microtest | TPP | Vision | Ref
GPL001 | Transactions sent from the GP Practice | Spine has no concept of GP Local Code and would prefer GP Requests to contain a pooled list code (GP Practice Code) and a dummy GMC Code. |  | Accept | Accept | ? | Action: Need to confirm | GPSoC001, GPSoC003, GPSoC010, GPSoC022
|  | GP Systems perform no validation on the authenticity of the GMC code |  | Accept | Accept | ? | Accept
|  | GMC Code must be a number of up to 7 digits and unique to the GP Local Code it is associated with |  | Accept | Accept | ? | Accept
|  | The GMC Code associated with a Pooled List code is set locally by the Practice (Usually '9999999') |  | Accept | Accept | ? | Action: Need to confirm
|  | Conversion of GP Local Code to GP Practice Code will be performed by Spine | GP Systems to convert all GP Local Codes to GP Practice Code on outgoing messages | Potential CCN | Potential CCN | ? | Potential CCN
|  | It’s not possible to re-use the ‘Transaction Number’ for GP Links messages when submitting an updated GP Links message |  | Accept | Accept | ? | Accept
GPL002 | Transactions sent from Spine to GP Practice (Note: Spine does not send MRS or MRF transactions) | Spine will send a valid GP Local Code with the associated GMC Code (unique at the practice to the GP Local Code). |  | Accept | Accept | ? | Accept | GPSoC002, GPSoC004, GPSoC005, GPSoC008
|  | The local code populated by Spine may not be the same as the code sent for that patient in the request from the GP Practice, if that Practice is still operating with GP Local Codes rather than a Pooled List code. |  | Accept | Accept | ? | Accept
|  | GP System will not validate the supplied GP Local Code and GMC Code other than to check that the GMC Code is correct for the supplied local code. The GP System does not validate the patient - GP Local code relationship |  | Accept | Accept | ? | Accept
|  | The response received from NHAIS must match for transaction number (for Approvals only) or NHS number (for all other transactions). The GP System does not validate patient - HA relationship other than for APF messages |  | Accept | Accept | ? | Accept
|  | Need to verify if and how the GP System uniquely identifies messages in the case where the GP Practice has multiple trading partners. Does it check the NHAIS Posting is appropriate for the supplied NHS Number? |  | ? | ? | ? | ?
|  | Spine will use a mechanism to ensure that we will not send two different payloads with the same interchange control number |  | Accept | ? | ? | Accept
GPL003 | Interchange Processing | If one transaction is invalid with format, the GP system fails all the transactions associated with the interchange. |  | Accept | Accept | ? | Accept | GPSoC006, GPSoC013, GPSoC014, GPSoC018, GPSoC020, GPSoC030, GPSoC032, GPSoC033, GPSoC040, GPSoC041
|  | If one transaction is invalid with data, GP System fails only that particular transaction and passes other valid transactions from the interchange. |  | Accept | Accept | ? | Accept
|  | Failed Interchanges can be tracked in the GP System Interchange Audit History |  | Accept | Accept | ? | ?
|  | GPSS receive/send interchanges in schedule manner through batches. |  | Accept | Accept | ? | Accept
|  | GP System will have no issue processing real time (not batched) GP Links interchanges. The GPSS would be under no obligation to process the increased number of interchange real time, but there would be an increase in the number of interchanges queued for processing when the mailbox is polled. |  | Accept | Accept | ? | Accept
|  | GP Systems are notified of interchange successes though the receiving of an incoming RECEP interchange Note: Our understanding from exercises mapping business processes with PCSE is that send failures are inferred from the absence of a RECEP message and that failure RECEP messages are not sent |  | Accept | Accept | ? | Accept
|  | There would be benefit in Spine also sending RECEP to the GP System Suppliers. To do this Spine could use the Spine Directory Service to determine the MESH mailboxes and NHS Digital's GPSoC National Tracking Database (which is the authoritive location where the services offered by, and the supplier of a clinical system of, one or more Practices may be ascertained) |  | Accept | Accept | ? | ?
|  | Interchange translation failures are notified to the GP Practices by email and telephone. The GP Practice then needs to notify the GP System Supplier if assistance is required to resolve the issue. |  | Accept | Accept | ? | Accept
|  | GPSS do not send RECEP failures so Spine would need to deduce failed interchanges based on absence of RECEP success |  | Accept | Accept | ? | Accept
|  | Duplicate interchanges received by the GP System sent to interchange history - GP Practice acknowledges to resolve Message sequence number not checked for duplicates Duplicate Transactions would not be applied. |  | Accept | Accept | ? | Accept
|  | Duplicate interchanges & transcations sent to unmatched box - not applied |  | Accept | ? | ? | Accept
|  | Spine will check interchange control number to identify missing interchanges, but dioes not check for missing messages or transactions |  | Accept | ? | ? | Accept
|  | GP Practice are required to set up their trading partners on the system. Practice are alerted if they receive an interchange from a trading partner not configured for their GP Practice |  | Accept | ? | ? | Accept
GPL004 | Close of Quarter Processing | The GP System will continue to function if Spine does not send a GP Links F8 End of Quarter marker message, but there may be an impact because GP Practices currently expect to receive an end of quarter notification to prompt them to close transctions for that quarter | GP Systems may need to work through business impact of this change with Practice an implement minor change to remove EoQ processing functionality | Potential CCN | Potential CCN | ? | Potential CCN | GPSoC007, GPSoC021
GPL005 | Address Updates | Spine cannot accept partial address updates because Spine addressescan be updated by many organisations and therefore it will be difficult to ensure the integrity of the update. GP System currently send a partial address for address amendments | GP Systems to be updated to send full address details for an address amendment (and full name for a name update) | Potential CCN | Potential CCN | ? | Potential CCN | GPSoC009, GPSoC016
|  | GP System can accept the full address from Spine to communicate address updates. |  | Accept | Accept | ? | Accept
|  | The GP System would benefit from also receiving the SCN relating to the address change and other patient demographic changes from Spine | The GP Links specification currently has no facility to contain the SCN, but it could possibly be supplied using a spare field. | Potential CCN | Potential CCN | ? | Potential CCN
|  | GP System current perform no PAF validation | Potential change request for GPSS to implement address integrity checking against PAF or a similar facility | Potential CCN | Potential CCN | ? | Potential CCN
|  | Majority of GP System addresses are source from Spine following a trace on patient record |  | Accept | Accept | ? | Accept
GPL006 | RI Codes | GP System does not validate/check/constrain the values populated in the RI field on outbound GP Links messages |  | Accept | Accept | ? | Action: Need to confirm | GPSoC011
|  | Gp System does validate that the RI code supplied on inbound messages is valid for the Trading Partner (NHAIS System). | GP Practice System to accept generic codes on messages sent from Spine - could be a manual activity to add this codes but error prone? | Potential CCN | Potential CCN | ? | Action: Need to confirm
|  | This will not prevent the adoption of simplified codes for care home residents and students, but will present a challenge on transition as patients with Local NHAIS codes indicating care home resident will need to be converted to the new unique 2 digit code | GP Systems to lock down RI codes entered to a limited set | Potential CCN | Potential CCN | ? | Action: Need to confirm
GPL007 | GP Notes | GP System current do not constrain what can be entered by the GP Practice in the GP Notes field of the GP Links Transaction | GP System to provide a drop down box of standard GP Notes appropriate to the request to reduce range of GP Notes supplied to PCS | Potential CCN | Potential CCN | ? | Potential CCN | GPSoC012
GPL008 | Integrity of GP System updates to Spine | The GP System send HL7 direct updates to Spine and the GP Links message systematically and does not allow one update to be sent but not the other | Vision stated that HL7 messages sent when sufficient data entered. The requirement for GP Links is higher and therefore this message may not be sent. Need to understand these situations | ? | ? | ? | Potential CCN - HL7 sent if sufficient data entered | GPSoC015, GPSoC034
|  | There are no Practices in England that use GP Links but no Direct Spine messaging |  | Accept | ? | ? | Accept
GPL009 | FP69 Notifications | The GP System shows the appropriate description for the code that is sent in with FP69 notifications. For example, for the reason code of 8, along with the supplied description. |  | ? | Accept | ? | Accept | GPSoC017
GPL010 | Previous HA Cypher | GP Practices populate the previous HA Cipher in a registration acceptance request with a value that represented the patients previous administrative area (i.e. Eng, Cym,IM, HJ, DMS, NI, SCT) (Wales code = CYM) |  | Accept | Accept | ? | Accept | GPSoC019
GPL011 | Title Field | GP System performs no validation on the value of title supplied in GP Links transactions |  | Accept | Accept | ? | Accept | GPSoC029
GPL012 | Character Set Vaidation | Spine will convert all GP Links message content to upper case |  | Accept | Accept | ? | Accept | GPSoC028
GPL013 | Practices using the same Link Code. | Spine can identify practices merged onto a common link code by using the GP Local Code supplied in the GP Link message and mapping to the associated Practice Code |  | Accept | ? | ? | Accept | GPSoC027
GPL014 | NHAIS MESH Mailbox | GPSS utilise or validate the GP-Links Source MESH Mailbox and / or Source Link code so Spine will spoof the NHAIS mailbox |  | Accept | ? | ? | Accept | GPSoC031
GPL015 | Deductions | No benefit in restricting the current use of GP Links messages. It would be more practical to implement these process changes when the GP Links convertor is replaced (ref - REG and DER messages with OOA reason for removal |  | Accept | Accept | ? | Accept | GPSoC035, GPSoC036, GPSoC037, GPSoC038, GPSoC039, GPSoC044, GPSoC045
|  | GP System can be updated to implement additional GP Links removal type code over and above the 3 currently used (1, 2, 13). This would require a change request to implement | GP Systems to implement additional UI to allow selection of additional removal reasons mapping to the GP Links removal type codes | Potential CCN | Potential CCN | ? | Potential CCN
|  | GP System does not validate the the deduction code but does display the details of the deductions |  | Accept | ? | ? | Accept
|  | GPSS handle the new HA / same GP secnario by sending a registration acceptance (anticipating a deduction response) |  | Accept | ? | ? | Accept
|  | In the scenario where a patient moves out of Practice area but re-registers under PoC scheme, the PCRM workflow will continue to require a patient deduction followed by re-registration |  | Accept | ? | ? | Accept
|  | DRR Messages sent from Spine to GP System will be displayed on a screen listing all the deduction rejections with the reason they were rejected |  | Accept | ? | ? | Accept
GPL016 | Blood and Organ Donor Preferences | GP System records the patient's blood and organ donor preferences using Clinical Codes |  | Accept | ? | ? | Accept | GPSoC047
GPL017 | Practice Splits and Mergers | Prior to a bulk transfer of patients within a Practice Split or Merger process, the source Practice will stop sending GP Links messages 5 days prior to the bulk transfer. How are Practice registrations and amendments recorded at the Practice in this period? |  | ? | ? | ? | ?
Note on E1: Matthews Neil: Some of these EMIS were due to confirm by looking at the code
Note on C2: Matthews Neil: Key word is prefer, so this is a could for the GPSS

## Candidate Change Requests
Change ID | Change Description | PCRM Priority | HJIS Priority | Clarification Reference | Edifact Specification Reference
CCN001 | GP Systems to convert all GP Local Codes to GP Practice Code on outgoing messages | Not Required | Not Required | GPL001 | N/A
CCN002 | GP Systems will no longer recieve an end of quarter message following transition from NHAIS to Spine. End of quarter processing will not be required from a central administrative perspective because the GP Payment calculation will no longer be controlled directly by GP Links registrations. How would this impact GP Practice Systems? | Required | Medium | GPL004 | Section 3.20 3.20 IN-COMING CLOSE OF QUARTER NOTIFICATION The Close of Quarter Processing consists of the Registration Close Quarter Notification (described in section 2.2.26), the Registration Quarterly Archives (section 2.2.27) and Quarterly Certificates and Capitation Reports (section 2.2.28)
CCN003 | GP Systems to be updated to send full address details for an address amendment and full name for a name update within a GP Links Amendment message | Required | High | GPL005 | Section 3.5 OUT-GOING MANUALLY-ENTERED AMENDMENTS Specification states: If at least one of the Address - Locality, Address - Post Town and Address - County fields is amended for a patient, then the values held for all three of these fields MUST be advised to the HA within the Amendment. This will assist in the process of "address coding" on the HA system We would like this rules extending so that all address lines are sent if any changes a made
CCN004 | The GP Links specification currently has no facility to contain the SCN, but it could possibly be supplied using a spare field. | Not Required | Not Required | GPL005 | N/A
CCN005 | GPSS to implement address integrity checking against PAF or a similar facility each time an address is amended on the GP System. Please see PDS Standard for updated specification | Required (Please see Edifact Specification notes for further detail) | Low | GPL005 | Whilst previously out of scope, the Programme now require this. An additional roadmap item is to follow to capture this, but it is included here as suppliers are more than welcome to develop this requirement alongside the others if more convenient for them. This is not a change for some of the suppliers. From a commercial perspective it is the removal of the contractual let rather than a change. The existing compliance requirements are: UPDADD-1 Local systems MUST be capable of deriving addresses from a PAF tool when performing updates. Must Systems must be able to utilise a PAF tool for address searching. UPDADD-1.1 When updating PDS with a PAF tool derived address, the PAF key MUST be included in the update.
CCN006 | GP Systems to lock down RI codes entered to a limited set consisting of a single unique two character code to indicate Nursing Home and a single unique two character code to indicate Student. The proposed new codes will be: V0 Nursing/Residential Care Homes Y0 Students Note: codes above contain 0 (zero) not O The approach for migration to the new codes has yet to be elaborated, but it is envisaged that action on the GP System and NHAIS will need to be co-ordinated to ensure that from an agreed time the codes specified above or blank are the only values that can be entered into the RI Code field by GP Practices. GPSS will continue to support the entry of the Service Personnel and Service Dependent codes from DMS Medical Centres This field currently appears as a drop down on the GP Practice Systems with the contents of the drop down configured directly by the Practice. Therefore this change is more about GPSS retricting this field to the national codes and overriding the local configuration. It was suggested that the field should be made mandatory with an option for N/A introduced | Required | Low | GPL006 | Section 3.2 STANDARD OUT-GOING REGISTRATION PROCESSING Residential Institute Code (N-M) Within EDIFACT Acceptance transactions, Acceptance standard forms and Archive files, the Residential Institute Code MUST: - Be a valid Residential Institute Code; i.e. the Code MUST be within the Table of Valid Residential Institute Codes for the patient's responsible HA (see section 4.3.4). As such, the Residential Institute Code MUST: • Have alphanumeric characters only. • Have a maximum length of 2 characters. • Have alphabetic characters in upper case We are not seeking to change this, just consolidate and restrict to use single national code for Care Home and Student rather than a multitude of local codes
CCN007 | GP System to provide a drop down box of standard free text appropriate to GP Links message types whilst allowing the GP Practice to still enter free text. Please see candidate set text options below: The GP System should encourage the user to select a standard text or enter nothing whilst still providing the option to enter free text | Required | Medium | GPL007 | Relevant to registrations, amendments and removal requests, but from the specification regarding removals: A free text field (GP Notes) MUST be provided allowing the GP to enter the precise reason for the Removal (Out of Area). Completion of this field will be mandatory if the patient corresponding to the Amendment is to be removed (out of area). This change only requests that GP Systems provide predefined text for common messages so that these can be processed automatically
CCN008 | Prevent situations where Direct HL7 messages are sent to Spine without the equivalemt GP Links messages being sent | Required | High | GPL008 | GP Systems to maintain integrity of Spine and NHAIS when changing patient data
CCN009 | GP Systems to remove any validation of NHS number against NHAIS posting. Spine has no concept of legacy NHAIS posting and can therefore only ever send a default NHAIS posting which might not match the NHS number for fringe Practices | Required | High | GPL008 | Section 3.3 IN-COMING AMENDMENT TRANSACTIONS Edificat specification states: The Amendment transactions received MUST be matched (by patient NHS Number; or by HA Cipher and NHS Number if the NHS number commences with the "?" character and, hence, represents a Query NHS number) This change just asserts that we cannot be sure that the HA Cipher included in the message from Spine will be correct for the NHS Number in the case where the GP Practice has multiple trading partners. Spine does not store the patients linked HA Cipher, so can only send the default associated with the GP Practice
CCN010 | GP Systems to implement additional UI to allow selection of additional removal reasons mapping to the GP Links removal type codes | Not Required | Not Required | GPL015 | N/A
CCN011 | GP System to make entry of the patient's previous administrative area (NHAIS Posting, may also be referred to in some organisations asTrading Partner code) mandatory for a registration transfer (i.e. Not including First Acceptances, Births, Immigrants, which will not have a previous admin area). Allowing the user to input values such as SCT for Scotland if the pattient has transferred in from Scotland, NI for Northern Ireland, CYM for Wales, IM for Ilse of Man and ENG for England or Unknown into this field | Required | Medium |  | Section 3.2 STANDARD OUT-GOING REGISTRATION PROCESSING Specification states: - The patient's previous responsible HA's Cipher MUST be included within the Previous HA Cipher field This change is requesting that post transition 'cipher' values are included in the list of valid cipher codes, these will be: ENG, CYM, IM, DMS and HJ. We would also like 'Unknown included so we can clearly determine when previous admin area isn't known

## Prev History
Change ID | Previous PCRM Priority on GPSoC CPR
CCN001 | Not Required
CCN002 | Medium
CCN003 | High
CCN004 | Not Required
CCN005 | Low
CCN006 | High
CCN007 | Medium
CCN008 | High
CCN009 | High
CCN010 | Not Required
CCN011 | Medium